## Index
Name of Your School: St Botolph's CE Primary School, Sleaford.
Schoool Music Development Plan | 2023/34
Priority | Objectives | Quantified targets (including milestones where appropriate)
To further develop the school's Music Curriculum offer so that the impact of the curriculum is explicitly ambitious for all pupils developing their musicality progressively | 1.1 Ensure that opportunities within the school music curriculum are aligned with the expectations of the National plan for music and allow children to make connections within their learning. 1.2 Refine Curriculum documentation so that the school's music curriculum is coherently planned and sequenced towards sufficiently mapped knowledge and developing skills over time - deliberate choices are explicit and end points/milestones are identified. 1.3 Strengthen medium term planning processes to enable teaching and learning to be adapted and refined as the journey of learning develops. 1.4 Develop a consistent lesson design so that key components (e.g. Rosenshine's Primciples of Instruction, retrieval practise and the guided practice model) of the curriculum intent are incorporated into all aspects of Teaching and Learning. 1.5 Develop and Implement Music Curriculum Assessment strategies so that teachers and subject leaders are clear on what the children have learnt, what knowledge they have remembered and what they can do. | By the end of Summer 2024 By Summer 2024 By Summer 2024 By the end of Summer 2024 By end of Summer 2024
To implement the expectations from the National Plan for Music Edcation so that all pupils to learn to sing, play an instrument and create music together, and have the opportunity to progress their musical interests and talents, including professionally. | 2.1 Timetabled curriculum music of at least one hour each week of the school year 2.2 Continue access to lessons across a range of instruments, and voice. 2.3 Continue school choir and/or vocal ensemble. 2.4 Develop a school ensemble/band/group. 2.5 Develop a space for rehearsals and individual practice. 2.6 Continue with a termly school performance. 2.7 Continue providing the opportunity to enjoy live performance at least once a year | yearly-ongoing ongoing Ongoing By Christmas 2024 By Christmas 2024 Ongoing Yearly, ongoing

## Priority 1
Priority | Objective | Action Ref. | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator comments
1 | 1.1 1.2 1.3 1.4 | 1.1.1 1.2.1 1.3.1 1.4.1 | Continue developing the Curriculum document based on feedback and ensure that spiralling curriculum is working. | SC | 2023-09-01 | 2024-08-01 | subject leader time 2 hour per term |  |  |  |  | Green
1 | 1.5 | 1.5.1 | Keep abreast of assessment developments as detailed in the SDP. | DW/SC | 2023-09-01 | 2024-04-01 | 0 |  |  |  |  | Amber
1 | [11 empty] | Red
1 | [11 empty] | Completed
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1 | [11 empty] | Red
1 | [11 empty] | Amber
Green
Completed

## Priority 2
Priority | Objective | Action Ref. | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Status: Progress and/or Impact | Evaluator comments
2 | 2.1. | 2.1.1 | check timetables to ensure music is being timetabled. | BM | 2023-09-01 | ongoing | Zero |  |  |  |  | Red | Not started yet
| 2.2 | 2.2.1 | WCIT in year 4 for ukulele 6 weeks | LMS/BM | 2024-01-01 | June/July 25 | funded by silver membership and 50% of costs covered by parents |  |  |  |  | Amber | In action
|  | 2.2.2 | Check musical instrument coverage in curriculum document. Ensure it aligns with an ambitious curriculum rather than varied experiences. | BM | 2024-01-01 | 2024-12-01 | subject leader time |  |  |  |  | Green | Nearly completed
| 2.3 | 2.3.1 | Choir every Monday after school | BM | 2023-09-01 | 2024-06-01 | zero |  |  |  |  | Completed
|  | 2.3.2 | Choir to visit Young Voices annually or Voices in A Million | BM | 8th feb 2024 | 8th Feb 2024 | Coach expenses
|  | 2.3.3 | Choir to visit care homes to forge local links | BM/DW | Early Feb 2024 | 2025-12-01 | none
| 2.4 | 2.4.1 | Discuss with head the possibility of paying for LMS to lead the ensemble | BM/DW | 2024-01-01 | 2025-04-01 | £45/Hour funded by parents
|  | 2.4.1 | Talk to Malcom Duckels (LMS) to discuss tutor availability | BM | 2024-01-01 | ongoing | zero
|  | 2.4.2 | Start ensemble | BM | 2024-09-01 | ongoing | see 2.4.1
| 2.5 | 2.5.1 | Speak to Head regarding Logistics | BM/DW | 2024-01-01 | 2024-01-01 | none
|  | 2.5.2 | Lunchtime rehearsal space set up and timetabled | BM | 2024-04-01 | ongoing | none
| 2.6 | 2.6.1 | Nativity Years 1 and 2 | Year 1 and 2 staff | 2023-12-01 | ongoing | License- £30
|  | 2.6.2 | Year 5 cantata | Year 5 | 2023-12-01 | ongoing | License-£30
|  | 2.6.3 | Year 4 Ukulele performance | Year 4 staff/ Vicky Carter | 2024-04-01 | ongoing | Funded by silver membership and parents
|  | 2.6.4 | Year 4 Easter Cantata | Year 4 staff | 2024-04-01 | ongoing | License-£30
|  | 2.6.5 | Year 6 production | Year 6 | 2024-07-01 | ongoing | License-£30
| 2.7 | 2.7.1 | RAF brass band to play to whole school | DW/BM | 19th dec | ongoing | none
|  | 2.7.2 | St George's band to play for us on tour | BM | 2024-07-01 | ongoing | none
|  | 2.7.3 | look into other visitors to play live music-Sleaford band/ other community bands | BM | 2024-01-01 | ongoing | none
|  | 2.7.4 | Set up a performance linking with other local school | BM | 2025-09-01 | Ongoing | none